## Task List
Sprint 7: AWS and deployment using Docker |  | 25/10/2019 to 4/11/2019
Github Repo: | https://github.com/nicklodeon10/FlightReservationSystem
Task List:
AWS
Technical Documentation
Presentation
Docker
Microservices

## Devang
Time for Completing Task
| Task | Alloted On | Estimated | Actual | Comments
1 | BU Comments | 25/10/2019 Friday | 4 hours | 3.5 hours
2 | Practical | 2019-01-11
| i.AWS |  | 4 hours | 4 hours
| ii.Implementation in project |  | 2.5 hours | 2.5 hours
3 | Practical | 2019-02-11
| i.Docker |  | 4 hours | 4 hours
| ii.Implementation in project |  | 2.5 hours | 2 hours

## Surya
Time for Completing Task
Task | Alloted On | Estimated | Actual | Comments
B U Comments | 2019-02-11 | 5 hours | 5 hours

## Navya
Time for Completing Task
| Task | Alloted On | Estimated | Actual | Comments
| B U Comments | 2019-02-11 | 5 hours | 5 hours
1 | Wireframe Design | 19/10/2019 Saturday | 3 hours | 3.5 hours | System Issues
| i) User Page |  | 0.5 hours | 0.5 hours
| ii) Admin Page |  | 0.5 hours | 0.5 hours
| iii) Add Flight |  | 0.5 hours | 0.5 hours
| iv)View Flight |  | 0.5 hours | 0.5 hours
| v)Search Flight |  | 0.5 hours | 0.5 hours
| vi)Modify Flight |  | 0.5 hours | 0.5 hours
2 | UI Design | 19/10/2019 Saturday | 4 hours | 4.5 hours | System Issues
| i)Admin Page |  | 1 hour | 1 hour
| ii) Add Flight |  | 1.5 hour | 1.5 hour
| iii)View Flight |  | 1 hour | 1 hour
| iv)Search Flight |  | 1 hour | 1 hour
| v)Modify Flight |  | 1 hour | 1 hour
3 | Recheck Spring Boot Restful | 19/10/2019 Saturday | 1 hour | 1 hour
4 | Integrate Angular with Spring Boot | 19/10/2019 Saturday | 1 hour | 1.5 hour | System Issues
5 | Pagination | 22/10/2019 Tuesday | 2 hours | 0.5 hour
6 | Validations | 22/10/2019 Tuesday | 3 hours | 3 hours
7 | Excel Upload | 22/10/2019 Tuesday | 2 hours | 2 hours
8 | Fixes | 23/10/2019 Wednesday | 3 hours | 3 hours