## Task List
Sprint 6: Spring Boot RESTful with Angular |  | 16/10/2019 to 24/10/2019
Github Repo: | https://github.com/nicklodeon10/FlightReservationSystem
Task List:
Wireframe Designing
Technical Documentation
Presentation
Angular Application
Spring Boot RESTful
JUnit Testing
Exception Handling
Security with JWT

## Devang
Time for Completing Task
| Task | Alloted On | Estimated | Actual | Comments
1 | Wireframe Design | 19/10/2019 Saturday | 2.5 hours | 1.5 hours
i | Home Page |  | 0.5 hours | 0.5 hours
ii | Find Bookings |  | 0.5 hours | 0.2 hours
iii | Enter Booking Details |  | 0.5 hours | 0.3 hours
iv | Booking Confirmation |  | 0.5 hours | 0.3 hours
v | View Bookings |  | 0.5 hours | 0.2 hours
2 | UI Design | 19/10/2019 Saturday | 3 hours | 3 hours
i | Home Page |  | 1 hour | 1.5 hours | System Issues
ii | Find Bookings |  | 0.5 hours | 0.5 hours
iii | Enter Booking Details |  | 0.5 hours | 0.5 hours
iv | Booking Confirmation |  | 0.5 hours | 0.5 hours
v | View Bookings |  | 0.5 hours | 0.5 hours
3 | Angular Application along with Integration | 19/10/2019 Saturday | 5 hours
i | Setup Application |  | 1 hour | 1 hour
ii | Home Page |  | 1 hour | 1.5 hours | System Issues
iii | Find Bookings |  | 1 hour | 1.5 hours | System Issues
iv | Enter Booking Details |  | 1 hour | 2.5 hours | System Issues
v | Booking Confirmation |  | 1 hour | 1 hour
vi | View Bookings |  | 1 hour | 1 hour
4 | Error Handling | 22/10/2019 Tuesday | 2 hours | 2 hours
5 | Pagination | 22/10/2019 Tuesday | 2 hours | 1.33 hours
6 | PDF Download | 22/10/2019 Tuesday | 2 hours | 2.5 hours | ¦Front End Error
7 | JWT | 22/10/2019 Tuesday | 3 hours | 6 hours | Logical Errors
8 | Validations | 22/10/2019 Tuesday | 2 hours | 2 hours
i | Search Available Flights |  | 1 hour | 1 hour
ii | Booking Details |  | 1 hour | 1 hour
9 | JWT Integration with Angular | 23/10/2019 Wednesday | 3 hours | 2.5 hours
10 | Integration | 23/10/2019 Wednesday | 1 hour | 1 hour
11 | UI Design | 23/10/2019 Wednesday | 2 hours | 1.5 hours
i | Log In and Sign Up |  | 2 hours | 1.5 hours
12 | Sign Up Functionality | 23/10/2019 Wednesday | 1.5 hours | 1.5 hours
13 | Other Changes | 23/10/2019 Wednesday | 2 hours | 2 hours

## Surya
Time for Completing Task
| Task | Alloted On | Estimated | Actual | Comments
1 | Wireframe Design | 19/10/2019 Saturday | 2.5 hours | 1.5 hour
| i) User Page |  | 0.5 hour | 0.5 hour
| ii) Admin Page |  | 0.5 hour | 0.5 hour
| iii) Add SFlight |  | 1 hour | 3 hour | Misconception in component,System Issues
| iv)View SFlight |  | 0.5 hour | 0.5 hour
| v)Search SFlight |  | 0.5 hour | 0.5 hour
2 | UI Design | 22/10/2019 Tuesday | 3.5 hours | 3 hour
| i)Admin Page |  | 1 hour | 1 hour
| ii) Add SFlight |  | 1 hour | 1 hour
| iii)View SFlight |  | 1 hour | 1 hour
| iv)Search SFlight |  | 0.5 hour | 0.5 hour
3 | Recheck Spring Boot Restful | 19/10/2019 Saturday | 1 hour | 1 hour
4 | Integrate Angular with Spring Boot | 19/10/2019 Saturday | 1 hour | 1.5 hour | System Issues
5 | Other Changes | 23/10/2019 Wednesday | 2 hours | 2 hours
6 | Debug and fix restful | 22/10/2019 Tuesday | 2 hours | 2.5 hours | Integration error
7 | Fixes | 23/10/2019 Wednesday | 4 hours | 4 hours

## Navya
Time for Completing Task
| Task | Alloted On | Estimated | Actual | Comments
1 | Wireframe Design | 19/10/2019 Saturday | 3 hours | 3.5 hours | System Issues
| i) User Page |  | 0.5 hours | 0.5 hours
| ii) Admin Page |  | 0.5 hours | 0.5 hours
| iii) Add Flight |  | 0.5 hours | 0.5 hours
| iv)View Flight |  | 0.5 hours | 0.5 hours
| v)Search Flight |  | 0.5 hours | 0.5 hours
| vi)Modify Flight |  | 0.5 hours | 0.5 hours
2 | UI Design | 19/10/2019 Saturday | 4 hours | 4.5 hours | System Issues
| i)Admin Page |  | 1 hour | 1 hour
| ii) Add Flight |  | 1.5 hour | 1.5 hour
| iii)View Flight |  | 1 hour | 1 hour
| iv)Search Flight |  | 1 hour | 1 hour
| v)Modify Flight |  | 1 hour | 1 hour
3 | Recheck Spring Boot Restful | 19/10/2019 Saturday | 1 hour | 1 hour
4 | Integrate Angular with Spring Boot | 19/10/2019 Saturday | 1 hour | 1.5 hour | System Issues
5 | Pagination | 22/10/2019 Tuesday | 2 hours | 0.5 hour
6 | Validations | 22/10/2019 Tuesday | 3 hours | 3 hours
7 | Excel Upload | 22/10/2019 Tuesday | 2 hours | 2 hours
8 | Fixes | 23/10/2019 Wednesday | 3 hours | 3 hours